## Sheet1
Task | Dependencies | Days needed | End Date | Done By
Request VMs,Network access ,Subdomain…etc. | -Waiting BTC users information -Vms information | 5 working days |  | Gov.sa
API Technical Specification document |  |  | Nov 27th | BTC
Signer Gateway deployment
Development of APIs for integration with Gov.sa and one Government Agency (as indicated by NCDC) for pushing data
Create list of documents View page | -BTC to provide us with API to retrieve the list of documents that need to be signed -BTC to send API contract (Technical specs) -API should be hosted and ready to consume in GSB/YSB | 10 working days | 11 th of Nov | Gov.sa
Request to sign documents | -Send documents ID with citizen KYC -BTC to send API contract (Technical specs) -API should be hosted and ready to consume in GSB/YSB | 15 working days | 25th Nov
Integration with emdha Trust Services |  |  | Nov 27th | BTC
Integration with NIC OTP service or other third-party OTP service for user notification and authentication
On successful deployment of Phase-I, the service will be enabled in production with few GA registrations through back-end process
SSO support and consultation |  | 5 working days |  | Gov.sa